Vendor Portfolio Review — Cost Reduction Opportunities

Date: March 31, 2026  |  Prepared for: CEO & CFO  |  Prepared by: VP of Operations

BOTTOM LINE

A 386-vendor, $7.9M annual spend audit has identified $905,000 in near-term, actionable savings across three initiatives. Salesforce UK Ltd — at $3.1M or 39.5% of total vendor spend — is the single highest-priority renegotiation target. CFO approval is required to begin vendor exit and renegotiations by April 2026.

KEY FINDINGS

- Spend concentration: Salesforce UK Ltd ($3.1M) accounts for 39.5% of total annual vendor spend, creating both significant negotiation leverage and single-vendor dependency risk.

- Facilities fragmentation: 122 vendors across $1.2M — under $10K per vendor average — including two overlapping Zagreb office leases totaling $328K (Zagrebtower + Weking D.O.O.).

- Tail vendor overload: 203 of 386 vendors (53%) are recommended for termination; the majority are sub-$5K annual lines that can be cut with minimal operational impact.

TOP 3 SAVINGS OPPORTUNITIES

- Salesforce Audit & Renegotiation — Est. $500,000 — Utilization audit and 15% contract reduction; consolidate HubSpot Ireland ($32K) into Salesforce native marketing automation.

- Global Facilities Consolidation — Est. $245,000 — Exit Weking D.O.O. Zagreb lease ($144K), terminate 40+ sub-$5K Croatian tail vendors (~$60K combined), and consolidate real estate advisors (JLL/CBRE).

- Finance & Audit Advisory Rationalization — Est. $160,000 — Terminate Grant Thornton ($46K) and Harmonic Group ($65K); migrate off Sage UK ($47K) to Planful; exit Cedar Recruitment ($19K).

IMPLEMENTATION TIMELINE

- Month 1–2: Terminate 200+ sub-threshold vendors; initiate Salesforce seat utilization audit; serve legal notice on Weking D.O.O. Zagreb lease.

- Month 3–4: Begin Salesforce contract renegotiation at renewal; wind down Grant Thornton and Harmonic Group engagements; consolidate Croatian vendor tail.

- Month 5–6: Complete Sage UK to Planful migration; finalize Zagreb real estate consolidation; exit Cedar Recruitment.

- Month 6+: Full $905K annualized savings realized; implement vendor governance policy to prevent tail re-growth.

RECOMMENDED ACTIONS

- Authorize vendor termination list (203 vendors) — Owner: VP Operations — April 2026

- Initiate Salesforce seat audit and renegotiation mandate — Owner: CFO / Finance — April 2026

- Issue notice on Weking D.O.O. Zagreb lease per contract terms — Owner: Procurement — April 2026

RISKS & CONSIDERATIONS

- Salesforce dependency: At $3.1M and 40% of total spend, renegotiation must protect service continuity; a parallel competitive evaluation (e.g. HubSpot) strengthens leverage without committing to migration.

- Contractual lock-in on facility leases: Zagreb exit is subject to local notice periods and early termination fees — legal review required before serving notice; net Year 1 savings may be lower than projected.

- Transition costs: Finance system migration (Sage to Planful) and advisory firm transitions carry one-time switching costs (~$15–25K), excluded from the $905K savings figure.

Auto Generated by AI with Confidence: HIGH  |  Source: Internal vendor spend data (12-month)  |  Reviewer: VP of Operations